## Gudiance Document
Responsible Party Codes
EHS | Environmental Health & Safety |  | IP | In Progress - Develop Procedures
CPDC | Capital Planning, Design & Construction |  | CMPLT | Complete
FS | Facilities Services |  | NTD | Need to Develop
PSS | Procurement & Support Services |  | N/A | Not Applicable
AA | Academic Affairs
HR | Human Resources - Training & Development
IT | Information Technology
PA | Public Affairs
Corresponding Permit Section
A.1.b.4.a: Overall Planning
A.1.b.4.b
PERMIT SECTION AND ELEMENT (Feb 5, 2013 Final) |  | Permit Compliance Year (June 30th Unless Otherwise Noted) | Permit Year | Responsible Implementing Party |  | Additional implementation notes (I.e., goals, milestones, etc.)
|  |  |  | Local MS4 Department | SIE, Regional Organization, OR Co-permittee
F.5.a | PROGRAM MANAGEMENT ELEMENT
F.5.a.1 | Legal Authority (update or create ordinance) | 2015 | 2 | CPDC |  | IP
F.5.b. | EDUCATION AND OUTREACH PROGRAM
F.5.b.1 | Select outreach option. If regional program, develop agreements | 2014 | 1 | CPDC |  | IP
F.5.b.2 | Public Outreach and Education
| Develop and implement comprehensive education and outreach program | 2015 | 2 | CPDC, PA, IT |  | IP
| Disseminate education materials to target audiences and translate as appropriate | 2015 | 2 | CPDC, PA, IT |  | IP
| Utilize public input in developing outreach program | 2015 | 2 | CPDC, PA, IT |  | IP
| Provide water efficient/ stormwater friendly landscaping information | 2015 | 2 | CPDC, PA, IT |  | IP
| Promote reporting of illicit discharges | 2015 | 2 | EHS, PA, IT |  | IP-Notice to employees about reporting any illicit discharges
| Provide pesticide/fertilizer application information |  |  | CPDC, PA, IT |  | CMPLT. Standards followed by FS
| Provide materials to school children | 2015 | 2 | EHS, PA, IT |  | CMPLT
F.5.b.3 | Staff and Site Operator Traning and Education: Illicit Discharge Detection and Elimination Training
| Develop and implement training program | 2016 | 3 | EHS,HR |  | CMPLT-Computer based training program available for all employees
F.5.b.4
| Biennial employee training | 2016 | 3 | EHS, HR |  | CMPLT
F.5.c | PUBLIC INVOLVEMENT AND PARTICIPATION PROGRAM
| Develop program with input of the public and implement | 2016 | 3 | CPDC, PA, IT |  | IP
F.5.d | ILLICIT DISCHARGE DETECTION AND ELIMINATION
F.5.d.1 | Outfall Mapping
| Create and maintain accurate outfall map including a site visit to each outfall | 2015 (Summer 2014) | 2 | CPDC, PA, IT |  | IP
F.5.d.2 | Field Sampling to Detect Illicit Discharges
| Sample ANY flowing outfalls while conducting F.5.d.1 | 2015 (Summer 2014) | 2 | EHS |  | IP-Sample preparations made
| Conduct followup investigation within 72 hours if action levels exceeded | 2015 (Summer 2014) | 2 | EHS |  | CMPLT
F.5.d.3 | Illcit Discharge Detection and Elimination Source Investigations and Corrective Actions
| Develop written proceedures for investigations and corrective actions | 2015 (Summer 2014) | 2 | CPDC |  | IP
| Once source of discharge is identified, req. responsible party to correct within 72 hours of notification and verify with follow-up investigation | 2015 (Summer 2014) | 2 | CPDC |  | IP
| Conduct followup investigation within 72 hours if action levels exceeded | 2015 (Summer 2014) | 2 | CPDC |  | IP
F.5.e | CONSTRUCTION SITE STORM WATER RUNOFF CONTROL PROGRAM
| Develop and implement and enforce program to prevent construction site discharges of pollutants. Include development of contract language requiring compliance with CGP | 2014 | 1 | CPDC |  | IP
F.5.f | POLLUTION PREVENTION/GOOD HOUSEKEEPING FOR PERMITTEE OPERATIONS PROGRAM
F.5.f.1 | Inventory of Permittee-Owned and Operated Facilities
| Develop and maintain inventory of ALL permittee owned or operated facilities that are a potential threat to water quality | 2015 | 2 | CPDC |  | IP
F.5.f.2 | Map of Permitte-owned or Operated Facilities
| Develop a map of inventoried facilities | 2015 | 2 | CPDC |  | IP
F.5.f.3 | Facility Assessment
| Conduct comprehensive annual assessment and identify subset of facilities that could be considered hotspots | 2016 | 3 | CPDC |  | IP
| Document comprehensive assessment procedures and results | 2016 | 3 | CPDC |  | IP
F.5.f.4 | Stormwater Pollution Prevention Plans
| Develop SWPPPS for hotspots | 2017 | 4 | CPDC, FS |  | IP
F.5.f.5 | Inspections, Visual Monitoring and Remdial Action
| Quarterly visually inspect hotspots | 2018 | 5 | EHS, CPDC |  | CMPLT
| Annual comprehensive hotspot inspection | 2018 | 5 | EHS, CPDC |  | CMPLT
| Quarterly hotspot visual observation of storm water and non-stormwater discharges | 2018 | 5 | EHS, CPDC |  | CMPLT
| Non-Hotspots - Inspect each inventoried facility that is not a hotspot once during permit | 2018 | 5 | EHS, CPDC |  | CMPLT
F.5.f.6 | Storm Drain System Assessment and Prioritization
| Implement proceedures to assess and prioritize maintenance of storm drain system infrastructure. And assign a priority to each facility based on accumulation of sediment, trash and/or debris | 2015 | 2 | FS |  | IP, cleaning out of all Dis in progress
F.5.f.7 | Maintenance of Storm Drain System
| Inspect storm drain systems based on assigned priorities. Inspect high priority catch basins annually | 2016 | 3 | FS |  | IP
| Clean high priority storm drains | 2016 | 3 | FS |  | IP
| Maintain surface drainage structures | 2016 | 3 | FS |  | IP
| Develop proceedure to dispose of waste materials removed from catch basins | 2016 | 3 | EHS |  | IP
F.5.f.8 | Permittee Operations and Maintenance Activities (O&M)
| Develop program to assess O&M activites for potential to discharge pollutants and inspect all O&M BMPs quarterly | 2016 | 3 | EHS |  | IP
F.5.f.9 | Landscape Design and Maintenance
| Implement a landscape design and maintenance program to reduce the amount of water, pesticides and fertilizers used by Permittees | 2015 | 2 | FS, CPDC |  | CMPLT
| Educate applicators and distributors of storm water issues | 2015 | 2 | FS, CPDC |  | IP
| Implement best practices to reduce pesticides and fertilizers | 2015 | 2 | FS, CPDC |  | IP
| Proper dispoal of unused chemicals | 2015 | 2 | FS, CPDC |  | IP
| Minimize irrigation run-off | 2015 | 2 | FS, CPDC |  | IP
F.5.g | POST CONSTRUCTION STORMWATER MANAGEMENT PROGRAM
F.5.g.1 | Site Design Measures
| Require implementation of site design measures on projects that create or replace 2,500-5,000 SF impervious area and parking lots | 2015 | 2 | FS, CPDC |  | IP
F.5.g.2 | LID Standards - all requlated projects shall implement LID standards to treat stormwater and provide baseline hydromod mgmt to meet numeric sizing criteria under F.5.g.2.b
| Implement standards on projects that create or replace >5,000 SF impervious area, aka Regulated Projects | 2015 | 2 | FS, CPDC |  | IP
| Road and Utility Projects creating 5,000 sf or more that are public or fall under planning authority of a city shall comply with LID except 85th % can follow EPA Guidance on green infrastructure | 2015 | 2 | FS, CPDC |  | IP
F.5.g.3 | Alternative Post-Construction Storm Water Management Program
| For multiple benefit projects a permittee may propose alternative Post Const. Requirements (ones that address water quality, supply, flood control, habitat enhancement, open space preserv, recreation, climate change) | No date provided - permittee may propose if desired |  | CPDC |  | IP
F.5.g.4 | Operation and Maintenance of Post-Construction Stormwater Management Measures
| Implement an O&M verification program for Regulated Projects | 2015 | 3 | CPDC |  | IP
F.5.h | PROGRAM EFFECTIVENESS ASSESSMENT
F.5.h.1 | Program Effectiveness Assesment and Improvement Plan (PEAIP)
| Submit PEAIP | 2015 | 2 | CPDC
F.5.h.2 | Storm Water Program Modifications
| Identify and summarize BMP and/or program modifications identified in priority program areas that will be made in the next permit term | 2018 | 5 | FS, CPDC |  | IP
F.5.i | TOTAL MAXIMUM DAILY LOADS COMPLIANCE REQUIREMENTS
F.5.i.1 | Comply with all approved TMDLs (Attachment G) | 2014 | 1 | CPDC |  | n/a
F.5.i.2 | Waste load allocations are incorporated herein by reference as enforceable parts of this Order | 2014 | 1 | CPDC |  | n/a
F.5.i.3 | Regional Board reviews TMDLs within one year of effective date and may propose modifications to requirements | 2014 | 1 | CPDC |  | checked with RWQCB no impact
F.5.i.4 | Reports status of implementation via SMARTS | 2014 | 1 | CPDC |  | IP
F.5.i.5 | Comply with Clean Water Act Sections 303d,306b and 314 | 2014 | 1 | CPDC |  | IP
F.5.j | ANNUAL REPORTING PROGRAM
F.5.j.2 | Use SMARTS to report and certify | 2014-2018 | all years | CPDC |  | IP
F.5.j.3 | Complete and retain annual reports and make available to RWQCB during working hours. | 2014-2018 | all years | CPDC |  | IP
F.5.j.4 | Submit detailed written or oral report to RWQCB if directed. | 2014-2018 | all years | CPDC |  | IP
F.5.j.5 | May coordinate reporting if regional programs | 2014-2018 | all years | CPDC |  | IP